## Sheet1
1 | Which decision-making model provides a framework for understanding complex problems and suggests different approaches based on the problem's context? | Cynefin Framework
2 | Which of the following project lifecycle models is considered to be a Flow-Based Agile approach? | Kanban
3 | Which of the following best describes the Waterfall model? | Linear and sequential
4 | Which software development approach emphasizes a continuous cycle of planning, executing, and evaluating? | Agile
5 | In the context of Lean Software Development, what does Value Stream Mapping primarily aim to achieve? | Identify and eliminate waste in the process
6 | What is the primary goal of the Sprint Review in Scrum? | Review the complete work and gather feedback
7 | Which of the following are key concepts in the Kanban methodology? (Select all that apply) | wip limits, kanban board
8 | True or False: The Waterfall model allows for changes to be easily incorporated during development. | FALSE
9 | In the context of Agile principles, which aspect is emphasized by "Responding to change over following a plan"? | Adaption to changing circumastnaces
10 | In a software development project, the team decides to prioritize working software over comprehensive documentation. This reflects which Agile principle? | Deliver value continuously
11 | Match correct matches for the Lean concepts and their descriptions? | b. Value Stream Mapping -> Identify waste and inefficiencies in the process. c. Cumulative Flow Diagram -> Visualize work in progress and identify bottlenecks.
12 | Which of the following are early Agile models? (Select all that apply) | Dynamic Systems Development Method (DSDM), Feature-Driven Development (FDD)
13 | Which project lifecycle model emphasizes continuous evaluation, risk management, and incremental development? | Spiral
14 | Which of the following are benefits of Agile methods? (Select all that apply) | Emphasis on individual interactions, Adaptable to changing requirements
15 | Match agile mindset with its chars. | Agile Mindset: Embracing change, Customer collaboration, Iterative development Bureaucratic Mindset: Rigid plans, Resistance to change, Sequential execution
16 | Which of the following are chars of the waterfall models ( select all that apply) | Minimal customer involvement, Sequential Phases
17 | Match scrum methedology with its desc | a. Sprint Retrospective -> Reflect on team processes and identify improvements. b. Sprint Planning -> Plan the work for the day and synchronize the team. c. Daily Scrum -> Review the completed work and gather feedback. d. Sprint Review -> Discuss progress with stakeholders and prioritize the backlog.
18 | In the context of software development, what does the acronym "SDLC" stand for? | Software Development Life Cycle
19 | Match the following chars with appropriate software dev approach | 1. Detailed project planning upfront -> **Waterfall model* 2. Adaptive to changing requirements -> **Agile methodologies** 3. Emphasis on customer collaboration -> **Agile methodologies**
20 | True or False: Agile methods emphasize rigid planning and documentation. | FALSE
21 | Match given scenaro with appropriate agile proceses | a. A team decides to reprioritize features based on changing market conditions. -> **Welcome changing requirements, even late in development** b. A team involves the customer in defining user stories and acceptance criteria. -> **Deliver value continuously** c. A project manager supports the team in removing obstacles and facilitating collaboration. -> **Build motivated teams** d. A team focuses on detailed documentation to ensure project success. -> **Comprehensive documentation**
22 | Match the following project example with dev approach | Creating a mobile app - Agile Launching a new satellite - Waterfall Construction of a bridge - Waterfall
23 | Which scenarios that demonstrate the application of Agile principles. (Select all that apply) | c. A project team holds daily stand-up meetings to discuss progress and challenges. d. A project team involves the customer throughout the development process to gather feedback.
24 | Match real life scenario with Agile principle being demonstrated. | a. A team holds a retrospective meeting after each iteration to discuss what went well and what could be improved. -> **Continuous improvement** b. A team delivers a minimum viable product to the customer for early feedback. -> **Customer collaboration** c. A team engages in daily collaboration and knowledge sharing to solve problems quickly. -> **Individuals and interactions**
25 | What is the primary advantage of Agile method over traditional…? | Early and continous delivery of valuable software